Research Plan Cross-Task Medical Knowledge Transfer with Small Language Models

Target Venues: NAACL, EACL, ACL BioNLP Workshop, *SEM Timeline: 16 weeks (4 months) Estimated GPU Budget: $380 – $780 Framework: PyTorch + HuggingFace Transformers + PEFT

Comprehensive Research Plan • February 2026

# 1. Executive Summary

This research investigates whether small language models (1B–8B parameters) can match or exceed the performance of large proprietary models on medical NLP tasks through cross-task knowledge transfer. By fine-tuning models on multiple SemEval clinical/biomedical tasks simultaneously using parameter-efficient methods (LoRA, QLoRA), we hypothesize that shared medical knowledge representations emerge that generalize better than task-specific fine-tuning.

The project addresses a critical gap: while GPT-4 and Med-PaLM achieve strong results on medical benchmarks, their size, cost, and data privacy concerns make them unsuitable for clinical deployment. This work demonstrates a practical path to competitive medical NLP with models that can run on a single consumer GPU.

Key Contributions 1. First systematic study of cross-task knowledge transfer for medical SemEval benchmarks using small LMs 2. Novel multi-task adapter architecture with medical domain-specific shared representations 3. Comprehensive benchmark: 5 SemEval tasks, 8 models, 3 training strategies, cost-performance analysis 4. Open-source release of fine-tuned models, adapters, and evaluation framework

# 2. Research Questions

- RQ1: Does multi-task fine-tuning across SemEval medical tasks improve performance compared to single-task fine-tuning for small language models?

- RQ2: Can parameter-efficient methods (LoRA/QLoRA) with shared adapters capture transferable medical knowledge across task types (NER, relation extraction, temporal reasoning)?

- RQ3: What is the performance-cost tradeoff between small multi-task models and large proprietary models (GPT-4, Med-PaLM) on medical NLP?

- RQ4: Which medical tasks benefit most from cross-task transfer, and what linguistic/medical features predict transfer success?

# 3. SemEval Tasks Selection

We select five SemEval tasks spanning different medical NLP capabilities. This diversity is essential for studying cross-task transfer.

| Task | Name | Type | Data Size | Prior SOTA |
| --- | --- | --- | --- | --- |
| 2014-T7 | Analysis of Clinical Text | NER + Normalization | ~500 notes | F1: 0.813 (UTH-CCB) |
| 2015-T14 | Disorder Identification | NER (discontiguous) | ~400 notes | F1: 0.757 (ezDI) |
| 2016-T12 | Clinical TempEval | Temporal reasoning | ~600 notes | F1: 0.843 (BluLab) |
| 2017-T3 | Community QA Medical | QA Retrieval | ~3K pairs | MAP: 0.882 (SimBow) |
| 2021-T6 | Clinical NER & RE | NER + Relations | ~500 docs | F1: 0.876 (BIOS) |

Data Access: Tasks 2014-T7, 2015-T14, and 2016-T12 use MIMIC clinical notes (requires PhysioNet credentialed access). Tasks 2017-T3 and 2021-T6 use publicly available data.

# 4. Model Selection & Architecture

## 4.1 Small Language Models (Primary Focus)

| Model | Params | Context | VRAM (FP16) | VRAM (4-bit) |
| --- | --- | --- | --- | --- |
| Phi-3-mini | 3.8B | 128K | ~8 GB | ~3 GB |
| Llama-3.2-3B | 3.2B | 128K | ~7 GB | ~2.5 GB |
| Gemma-2-2B | 2.6B | 8K | ~6 GB | ~2 GB |
| Mistral-7B-v0.3 | 7.2B | 32K | ~15 GB | ~5 GB |
| Llama-3.1-8B | 8B | 128K | ~17 GB | ~6 GB |
| BioMistral-7B | 7.2B | 32K | ~15 GB | ~5 GB |

## 4.2 Baselines & Comparisons

- GPT-4o / GPT-4o-mini (via API, zero-shot and few-shot prompting)

- PubMedBERT / BioBERT / ClinicalBERT (encoder-only fine-tuning baselines)

- Original SemEval task winners (as reported in proceedings)

## 4.3 Multi-Task Architecture

We propose a Shared-Private Adapter architecture:

- Shared Medical Adapter: A LoRA adapter trained on all tasks simultaneously, capturing general medical language understanding (clinical abbreviations, drug names, anatomical terms, temporal expressions)

- Task-Specific Adapters: Lightweight per-task LoRA modules that capture task-specific patterns (e.g., discontiguous entity boundaries for NER, temporal relation labels)

- Fusion Layer: Learned attention-based combination of shared + private adapter outputs

This is inspired by AdapterFusion (Pfeiffer et al., 2021) but adapted for the medical multi-task setting with asymmetric task importance weighting.

# 5. Experimental Design

## 5.1 Training Strategies (Ablation Matrix)

| Strategy | Description | Adapter Setup | Purpose |
| --- | --- | --- | --- |
| S1 | Single-task fine-tuning | 1 LoRA per task | Baseline |
| S2 | Multi-task simultaneous | 1 shared LoRA, all tasks | Test shared representations |
| S3 | Shared + Private adapters | Shared LoRA + per-task LoRA | Novel architecture (ours) |
| S4 | Sequential transfer | Pre-train shared, then adapt | Curriculum learning |
| S5 | QLoRA (4-bit) multi-task | Quantized base + adapters | Memory efficiency |

## 5.2 Hyperparameter Search Space

| Parameter | Range | Search Method |
| --- | --- | --- |
| Learning rate | {1e-5, 2e-5, 5e-5, 1e-4} | Grid search |
| LoRA rank (r) | {8, 16, 32, 64} | Grid search |
| LoRA alpha | {16, 32, 64} | Tied to rank (2x r) |
| Batch size (effective) | {16, 32} | With grad accumulation |
| Epochs | {3, 5, 10} | Early stopping (patience=3) |
| Task sampling ratio | Proportional / Uniform / Sqrt | Grid search |
| Warmup ratio | {0.05, 0.1} | Fixed |

## 5.3 Evaluation Metrics

- Primary: Task-specific metrics (F1 for NER/RE, MAP for QA) matching original SemEval evaluations

- Aggregate: Average normalized score across all 5 tasks

- Efficiency: FLOPs per inference, latency (ms), peak VRAM, trainable parameters

- Cost: USD per 1000 inferences (GPU cost for small models vs. API cost for GPT-4)

- Transfer: Performance delta between multi-task and single-task (positive = beneficial transfer)

- Statistical: Bootstrap confidence intervals (95%), paired permutation tests for significance

# 6. GPU Costs & Compute Budget

## 6.1 GPU Platform Comparison

| Platform | GPU | VRAM | Price/hr | Notes |
| --- | --- | --- | --- | --- |
| Google Colab Pro+ | A100 | 40 GB | $49.99/mo | Best value |
| RunPod | A100 80GB | 80 GB | $1.64/hr | Flexible, on-demand |
| Lambda Labs | A100 80GB | 80 GB | $1.10/hr | Often sold out |
| Vast.ai | A100 40GB | 40 GB | $0.80–$1.20/hr | Cheapest spot |
| AWS (p4d) | A100 40GB | 40 GB | $3.06/hr | Reliable, expensive |
| Kaggle (Free) | T4 / P100 | 16 GB | Free (30hr/wk) | For small models only |

## 6.2 Detailed Compute Estimates

All estimates assume a single A100 40GB GPU. Training times include hyperparameter search with early stopping.

| Experiment | GPU Hrs | Runs | Total Hrs | Vast.ai | RunPod |
| --- | --- | --- | --- | --- | --- |
| Phase 1: Data & Baseline |  |  |  |  |  |
| BERT baselines (5 tasks) | 0.5 | 5 | 2.5 | $2.50 | $4.10 |
| BioBERT/ClinicalBERT (5 tasks) | 0.5 | 10 | 5 | $5.00 | $8.20 |
| Phase 2: Single-Task (S1) |  |  |  |  |  |
| LoRA fine-tune (6 models x 5 tasks) | 2 | 30 | 60 | $60 | $98.40 |
| Hyperparam search (top 3 models) | 1.5 | 45 | 67.5 | $67.50 | $110.70 |
| Phase 3: Multi-Task (S2–S4) |  |  |  |  |  |
| Multi-task training (3 strategies) | 4 | 9 | 36 | $36 | $59.04 |
| Adapter fusion experiments | 3 | 9 | 27 | $27 | $44.28 |
| Phase 4: Quantization (S5) |  |  |  |  |  |
| QLoRA 4-bit training (best 3 models) | 2 | 15 | 30 | $30 | $49.20 |
| GPTQ/AWQ post-quant eval | 0.5 | 18 | 9 | $9 | $14.76 |
| Phase 5: GPT-4 Baselines |  |  |  |  |  |
| GPT-4o API calls (5 tasks) | — | — | — | $40–$80 | (API cost) |
| Buffer (debugging, reruns) |  |  | 30 | $30 | $49.20 |
| TOTAL |  |  | ~267 hrs | $307–$387 | $438–$518 |

## 6.3 Recommended Budget Plan

Budget Strategy: Tiered Approach Tier 1 – Budget ($380): Colab Pro+ ($50/mo x 4) + Vast.ai spot (~$180 for overflow) Tier 2 – Standard ($580): RunPod on-demand A100 (~$440) + GPT-4 API (~$60) + Colab ($80) Tier 3 – Comfortable ($780): Lambda Labs reserved ($300) + RunPod ($240) + GPT-4 API ($80) + buffer ($160) Tip: Use Kaggle (free T4) for data preprocessing, small model prototyping, and BERT baselines. Reserve cloud GPUs for LLM fine-tuning only. This can save 20–30 GPU hours.

# 7. Project Timeline (16 Weeks)

| Week | Activities | Deliverables | GPU Hours |
| --- | --- | --- | --- |
| 1–2 | Literature review, data access (PhysioNet), preprocessing pipelines | Data loaders, EDA report | ~5 hrs (free tier) |
| 3–4 | BERT/BioBERT baselines on all 5 tasks, reproduce prior SOTA | Baseline results table | ~8 hrs |
| 5–7 | Single-task LoRA fine-tuning for all 6 small LMs across 5 tasks | S1 results, best models identified | ~128 hrs |
| 8–10 | Multi-task experiments (S2–S4), adapter fusion, transfer analysis | Transfer matrix, ablation results | ~63 hrs |
| 11–12 | Quantization experiments (S5), GPT-4 API baselines, efficiency benchmarks | Full results table, cost analysis | ~39 hrs + API |
| 13–14 | Error analysis, transfer heatmaps, ablation studies, statistical tests | Figures, analysis notebook | ~10 hrs |
| 15–16 | Paper writing, open-source release, model uploads to HuggingFace | Camera-ready paper, GitHub repo | ~5 hrs |

# 8. Expected Results & Novelty Arguments

## 8.1 Hypothesized Outcomes

- H1: Multi-task small LMs (S3) will outperform single-task (S1) by 2–5 F1 points on average, with largest gains on low-resource tasks (2015-T14, 2017-T3)

- H2: The best small LM configuration (Llama-3.1-8B with S3) will achieve within 3 F1 points of GPT-4 zero-shot, at 50–100x lower inference cost

- H3: 4-bit quantized multi-task models retain 95%+ of full-precision performance while reducing VRAM by 3–4x

- H4: Transfer is asymmetric: NER tasks transfer well to each other, but temporal reasoning transfers poorly to NER

## 8.2 Novelty Arguments for Reviewers

Unlike prior work that evaluates LLMs on medical tasks individually, this work is the first to study cross-task medical knowledge transfer with parameter-efficient adapters on SemEval benchmarks. Key differentiators:

- Scale of comparison: No existing work compares 6+ small LMs across 5 medical tasks with 5 training strategies

- Practical focus: Cost-performance analysis rarely appears in NLP papers but is critical for clinical adoption

- Reproducibility: Full open-source release (code, models, adapters, evaluation scripts)

- Adapter architecture: Shared-private medical adapter design is novel for this setting

# 9. Publication Strategy

| Venue | Type | Deadline | Focus | Acceptance |
| --- | --- | --- | --- | --- |
| ACL BioNLP | Workshop (main conf.) | ~Mar 2026 | Full results | ~35% |
| EMNLP | Main + Findings | ~Jun 2026 | Full paper | ~23% + Findings |
| NAACL | Main + Findings | ~Oct 2026 | Full paper | ~25% |
| *SEM | Co-located workshop | ~Mar 2026 | Analysis focus | ~40% |
| LREC-COLING | Conference | Varies | Benchmark paper | ~45% |

Recommended path: Submit to BioNLP workshop first (higher acceptance, good feedback), then expand to EMNLP or NAACL main conference with additional experiments.

# 10. Codebase Structure (PyTorch)

The project uses PyTorch, HuggingFace Transformers, and PEFT. Below is the recommended repository structure:

| Path | Description |
| --- | --- |
| src/data/ | Task-specific data loaders (SemEval format parsers) |
| src/models/adapters.py | Shared-Private adapter architecture, fusion layer |
| src/models/heads.py | Task-specific heads (token classification, sequence classification, QA) |
| src/training/trainer.py | Multi-task trainer with dynamic task sampling |
| src/training/quantize.py | QLoRA, GPTQ, AWQ quantization pipelines |
| src/eval/metrics.py | Task metrics, bootstrap CIs, significance tests |
| src/eval/efficiency.py | FLOPs counter, latency profiler, VRAM tracker |
| configs/ | YAML configs for each experiment (model, task, strategy) |
| scripts/run_experiment.py | Main entry point with Hydra config management |
| notebooks/ | Analysis, visualization, transfer heatmaps |

## 10.1 Key Dependencies

| Package | Version | Purpose |
| --- | --- | --- |
| torch | >=2.2 | Core framework |
| transformers | >=4.40 | Model loading, tokenizers |
| peft | >=0.10 | LoRA, QLoRA adapters |
| bitsandbytes | >=0.43 | 4-bit quantization |
| auto-gptq | >=0.7 | GPTQ quantization |
| autoawq | >=0.2 | AWQ quantization |
| datasets | >=2.18 | Data loading and processing |
| wandb | >=0.16 | Experiment tracking |
| hydra-core | >=1.3 | Config management |
| seqeval | >=1.2 | NER evaluation |

# 11. Risk Mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| PhysioNet data access delayed | Medium | Blocks 3 of 5 tasks | Apply early; start with public tasks (2017-T3, 2021-T6) |
| Small LMs underperform on all tasks | Low | Weak results narrative | Pivot to “when do small models fail” analysis angle |
| No transfer benefit observed | Medium | Core hypothesis invalidated | Negative result is still publishable; analyze why transfer fails |
| GPU budget overrun | Medium | Cannot complete experiments | Use Kaggle for prototyping; reduce model count to top 3 |
| Scooped by concurrent work | Low | Reduced novelty | Focus on unique adapter architecture and cost analysis |

# 12. Key References

Hu et al. (2022). LoRA: Low-Rank Adaptation of Large Language Models. ICLR.

Dettmers et al. (2023). QLoRA: Efficient Finetuning of Quantized Language Models. NeurIPS.

Pfeiffer et al. (2021). AdapterFusion: Non-Destructive Task Composition for Transfer Learning. EACL.

Singhal et al. (2023). Large Language Models Encode Clinical Knowledge. Nature.

Labrak et al. (2024). BioMistral: A Collection of Open-Source Pretrained LLMs for Medical Domains. ACL Findings.

Nori et al. (2023). Can Generalist Foundation Models Outcompete Special-Purpose Tuning? arXiv.

Lee et al. (2020). BioBERT: A Pre-trained Biomedical Language Representation Model. Bioinformatics.

Bethard et al. (2016). SemEval-2016 Task 12: Clinical TempEval. SemEval Workshop.

Elhadad et al. (2015). SemEval-2015 Task 14: Analysis of Clinical Text. SemEval Workshop.

Suominen et al. (2013). Overview of the ShARe/CLEF eHealth Evaluation Lab. CLEF.

I'm building a research project: "Cross-Task Medical Knowledge Transfer with Small Language Models."

Read every CLAUDE.md file in this repo carefully — they contain the full research plan, architecture specs, experiment configs, training protocols, and evaluation procedures. The root CLAUDE.md is the master orchestration file.

Project Context

We study whether multi-task fine-tuning of small LMs (2B–8B) on medical SemEval tasks enables genuine cross-task knowledge transfer (not just data exposure). The core falsifiable claim: if multi-task models outperform single-task models when total training tokens are equalized, this constitutes evidence of real transfer.

Key constraints:

- All training runs on free Kaggle T4 (16 GB VRAM) — budget is $0–$80

- QLoRA 4-bit for 7–8B models, FP16 LoRA for 2–3B models

- Every run must checkpoint every 200 steps (Kaggle sessions die without warning)

- Every run must log cumulative tokens per task (required for the token-controlled baseline, RQ5)

What I Need You to Do Now (Phase 0 — Foundation)

Implement the project foundation in this order. After each file, briefly confirm what you built and any design decisions you made.

Step 1: Repository Setup

- Initialize the full directory structure from CLAUDE.md

- Create requirements.txt with pinned versions:

torch>=2.2.0

transformers>=4.40.0

peft>=0.10.0

bitsandbytes>=0.43.0

datasets>=2.18.0

accelerate>=0.28.0

wandb>=0.16.0

hydra-core>=1.3.0

omegaconf>=2.3.0

seqeval>=1.2.2

scikit-learn>=1.4.0

scipy>=1.12.0

numpy>=1.26.0

pandas>=2.2.0

tqdm>=4.66.0

- Create setup.py with package metadata

- Create a basic README.md

Step 2: Core Data Module (src/data/)

Implement in this order, following src/data/CLAUDE.md:

- src/data/base.py

  - UnifiedSample dataclass with fields: task, task_type, task_level, input_text, labels, metadata, token_count

  - BaseTaskDataset abstract class with parse(), to_unified(), __len__, __getitem__

  - TaskRegistry to register and retrieve task datasets by name

- src/data/multitask_loader.py

  - MultiTaskBatchSampler with three sampling strategies: proportional, uniform, temperature-scaled (τ parameter)

  - TokenTracker class that logs cumulative tokens per task per step — this is critical for RQ5

  - The sampler must support resuming from a specific step (for Kaggle checkpoint resume)

- src/data/collators.py

  - NERCollator — pads input_ids, attention_mask, and BIO label sequences

  - SpanCollator — for discontiguous entities (Task 2015-T14), handles span candidate generation

  - RECollator — pads entity pairs and relation labels

  - QACollator — pads question-answer pairs with relevance labels

  - Each collator must handle variable-length sequences efficiently

- Task parsers — implement stubs with clear docstrings and TODO markers for the actual parsing logic (since we don't have the data files yet):

  - src/data/semeval2014t7.py — BRAT annotation parser → BIO tags

  - src/data/semeval2015t14.py — MUST use span-based format, not BIO (discontiguous entities)

  - src/data/semeval2016t12.py — temporal relation triples (EVENT, TIMEX, TLINK)

  - src/data/semeval2017t3.py — QA pair ranking

  - src/data/semeval2021t6.py — combined NER + RE (has both Level 1 and Level 2 components)

Step 3: Utility Module (src/utils/)

- src/utils/auto_batch.py

  - find_optimal_batch_size(model, sample_batch_fn, min_bs, max_bs, target_util=0.85)

  - Binary search for max batch size that fits in VRAM

  - Must handle OOM gracefully with gc.collect() and torch.cuda.empty_cache()

  - Print GPU name, total VRAM, and utilization percentage

- src/utils/vram_monitor.py

  - VRAMMonitor class that checks every N steps

  - Detects VRAM leaks (alerts if peak grows by >0.5 GB between checks)

  - Detects loss explosion (NaN or >100)

  - Estimates ETA based on rolling average step time

- src/utils/checkpoint.py

  - CheckpointManager that saves LoRA adapters only (10–50 MB, not full model)

  - Saves optimizer state, scheduler state, step count, epoch, best metric, token counts per task

  - save() every N steps, load_latest() to resume

  - Keeps only last 2 checkpoints to save disk space

  - Designed for Kaggle's /kaggle/working/ directory (20 GB limit)

- src/utils/smoke_test.py

  - smoke_test(model, train_loader, n_steps=50)

  - Trains on ~100 samples for 50 steps

  - Checks: loss decreased by >50%, no NaN, no explosion, reasonable range

  - Returns bool — if False, kill the run immediately

Step 4: Model Loading (src/models/base_loader.py)

- load_model(model_name, task_type, quantization_config, gradient_checkpointing)

- Auto-decides QLoRA vs FP16 based on parameter count (>4B → QLoRA)

- Applies BitsAndBytesConfig for quantization

- Enables gradient checkpointing for 7B+ models

- Tries Flash Attention 2, falls back gracefully

- Sets PYTORCH_CUDA_ALLOC_CONF=expandable_segments:True

- Returns (model, tokenizer, is_quantized)

Design Principles to Follow

- Type hints everywhere — all function signatures must be typed

- Dataclasses for configs — no raw dicts floating around

- Pathlib, not os.path — modern Python file handling

- Every public function gets a docstring — explain what, why, and any gotchas

- Assert parameter parity — any function that creates model variants must verify trainable param counts match within 5%

- Token counting is a first-class citizen — the TokenTracker must be integrated into every training path, not bolted on later

- Kaggle-first design — assume the session will die. Design for resume.

- Log everything to wandb — but make wandb optional (offline mode for debugging)

What NOT to Do Yet

- Don't implement the adapter architectures yet (that's Phase 1)

- Don't implement the training loop yet (that's Phase 1)

- Don't implement evaluation metrics yet (that's Phase 2)

- Don't download any models or data yet

- Don't create Hydra configs yet (we'll do that after the code modules are stable)

After You're Done

Tell me:

- What you built and any design decisions you made

- Which files have TODO markers that need real data to complete

- Whether any dependency versions conflict

- Estimated time to run pytest on the foundation (should be <30 seconds with mocked data)

Step 5: Results Management (src/results/)

Read src/results/CLAUDE.md carefully. This system is the backbone of the entire project — every experiment saves its results here, the token-controlled baseline reads from here, and paper tables are auto-generated from here.

- src/results/schema.py Define all result dataclasses with @dataclass and JSON serialization:

  - ExperimentResult — top-level container for one experiment run

  - TrainingStats — steps, epochs, tokens_per_task (dict), total_tokens, training_time, peak_vram, early_stopped

  - TaskMetrics — primary_metric, primary_metric_name, secondary_metrics (dict), confidence_interval (tuple)

  - EfficiencyStats — inference_latency_ms, throughput, peak_vram, trainable_params, cost_per_1k

  - CalibrationStats — ece, bin_accuracies, bin_confidences, bin_counts

  - ContaminationResult — zero_shot_f1, ngram_overlap, min_k_p_value, overall_contaminated

  - GradientConflictStats — conflict_frequency (dict of dict), total_conflicts, total_steps

Every dataclass must have:

  - to_dict() method for JSON serialization

  - from_dict(d) classmethod for deserialization

  - Timestamp auto-set on creation

- src/results/manager.py Implement ResultsManager class: Save operations (called after every eval and end of training):

  - save_result(result: ExperimentResult) -> Path — saves JSON to correct phase directory

  - save_checkpoint(model, result: ExperimentResult) -> Path — saves LoRA adapter weights + metadata

  - Auto-creates directory structure on first save

Load operations (called by downstream analysis):

  - load_result(experiment_id: str) -> ExperimentResult

  - load_all_results(phase=None, strategy=None, model=None, task=None) -> list[ExperimentResult]

  - Filter by any combination of phase/strategy/model/task

Query operations (called by TokenControlledTrainer and paper generation):

  - get_token_count(strategy, model) -> dict[str, int] — returns tokens_per_task from a multi-task run. This is CRITICAL for RQ5: the token-controlled baseline calls this to know how many tokens to train on.

  - get_best_result(strategy, model, task) -> ExperimentResult — best by primary metric

  - get_baseline_score(model, task) -> float — S1 single-task score

Aggregation operations (called by generate_paper_tables.py):

  - build_main_results_table() -> pd.DataFrame — strategies × tasks pivot

  - build_transfer_matrix() -> np.ndarray — 5×5 for heatmap

  - build_pareto_frontier() -> pd.DataFrame — cost vs performance

  - build_token_comparison() -> pd.DataFrame — multi-task vs token-controlled (RQ5)

  - build_ablation_table() -> pd.DataFrame — A1–A4 with param counts

Paper generation:

  - generate_latex_tables(output_dir) — auto-generates LaTeX booktabs tables

  - generate_figure_data(output_dir) — exports JSON/CSV for matplotlib

Integrity check:

  - validate_all() -> dict — lists which experiments are missing, incomplete, or have mismatched token counts

- src/results/latex_generator.py

  - generate_main_table(df) -> str — LaTeX booktabs for Table 1 (strategies × tasks)

  - generate_efficiency_table(df) -> str — Table 2 (latency, VRAM, cost, ECE)

  - generate_ablation_table(df) -> str — Table 3 (A1–A4)

  - generate_error_table(df) -> str — Table 4 (error categories)

  - Bold the best score per column, underline second-best

  - Include ± std when 3-seed results available

  - Include significance markers (* p<0.05, ** p<0.01)

Design rules:

- Every save_result() call writes to disk immediately (no buffering). This is insurance against Kaggle session death.

- JSON files are human-readable with indent=2.

- File naming follows the convention in src/results/CLAUDE.md.

- The results/ directory should work both on Kaggle (/kaggle/working/results/) and locally (./results/). Use a configurable base path.

- All aggregation functions should be idempotent — re-running them just overwrites the aggregated files.

Then I'll give you the Phase 1 prompt for model architectures.

PHASE 1 PROMPT — Use After Phase 0 Is Complete

Phase 0 foundation is complete. Now implement the model architectures.

Read src/models/CLAUDE.md carefully. Implement in this order:

Step 1: src/models/adapters.py

- SharedPrivateLoRA — shared adapter (r=16) + per-task private adapters (r=8)

- AttentionFusion — learns to weight shared vs private outputs

- GatedResidualFusion — alternative: gate * shared + (1-gate) * private

- Helper: count_trainable_params(model) for parameter parity verification

Step 2: src/models/hierarchical.py

- HierarchicalMTLModel — the primary architectural novelty

- Level 1 (NER tasks) → Level 2 (RE/QA tasks) cascade

- CrossLevelAttention module connecting Level 1 features to Level 2

- Option to detach L1 gradients (ablation flag)

Step 3: src/models/heads.py

- TokenClassificationHead — standard BIO tagging (Tasks 2014-T7, 2021-T6 NER)

- SpanClassificationHead — span enumeration + linking for discontiguous entities (Task 2015-T14)

- RelationExtractionHead — entity pair classification (Tasks 2016-T12, 2021-T6 RE)

- SequenceRankingHead — pairwise ranking for QA (Task 2017-T3)

Step 4: src/models/multitask_model.py

- MultiTaskModel — wraps base model + adapters + heads

- Routes inputs to correct head based on task_type

- Supports all 6 strategies (S1–S5, S3b) via config

Step 5: Architecture Ablation Support

- Implement factory function create_ablation_variant(variant: str, base_model, config) for A1–A4

- A1: Shared only (r=24), A2: Private only (r=24), A3: Shared+Private (no fusion), A4: Full model

- ASSERT parameter parity — all variants within 5% of target param count

- Add unit test that creates all 4 variants and checks param counts match

After you're done, tell me the trainable param counts for each variant (for Llama-3.2-3B as the example model).

PHASE 2 PROMPT — Use After Phase 1 Is Complete

Phase 1 architectures are complete. Now implement training and evaluation.

Read src/training/CLAUDE.md and src/evaluation/CLAUDE.md carefully.

Step 1: src/training/loss.py

- UncertaintyWeightedLoss — learns per-task weights via homoscedastic uncertainty (Kendall 2018)

- EqualWeightedLoss — simple average (ablation baseline)

Step 2: src/training/pcgrad.py

- PCGradOptimizer — Projected Conflicting Gradients (Yu et al., 2020)

- Must log conflict frequency between each task pair (for RQ4 negative transfer analysis)

- Wrap any standard optimizer (AdamW)

Step 3: src/training/trainer.py

- MultiTaskTrainer extending HuggingFace Trainer

- Integrates: TokenTracker, VRAMMonitor, CheckpointManager, PCGrad, uncertainty loss

- Supports all strategies via config flag

- TokenControlledTrainer subclass that stops training when target token count is reached (RQ5)

Step 4: src/training/callbacks.py

- VRAMCallback — monitors VRAM every 50 steps

- QuickEvalCallback — evaluates on 500 dev samples every 200 steps

- TokenLoggingCallback — logs cumulative tokens per task to wandb

- GradientConflictCallback — logs PCGrad conflict frequency

Step 5: src/evaluation/metrics.py

- compute_task_metrics(task_name, predictions, labels) — dispatches to correct metric

- bootstrap_ci(scores, n_bootstrap=10000) — 95% confidence intervals

- paired_permutation_test(scores_a, scores_b) — significance testing

- wins_ties_losses(method_a, method_b, threshold=0.5) — per-task comparison

Step 6: src/evaluation/contamination.py

- ContaminationChecker with three layers: zero-shot audit, n-gram overlap, Min-K% probing

- Returns per-model-task contamination report

Step 7: src/evaluation/calibration.py

- expected_calibration_error(confidences, predictions, labels, n_bins=15)

- plot_reliability_diagram(confidences, accuracies) — for paper Figure 5

Step 8: src/evaluation/probing.py

- LinearProbe(hidden_dim, num_classes) — single linear layer on frozen adapter representations

- evaluate_adapter_probes(model, adapter_name, probe_datasets) — runs all 4 probes

Step 9: src/evaluation/transfer_analysis.py

- compute_transfer_matrix(single_task_results, multi_task_results) — 5×5 heatmap data

- label_schema_similarity(task_a, task_b) — for RQ4

- vocabulary_overlap(task_a_data, task_b_data) — for RQ4

- detect_negative_transfer(st_scores, mt_scores) — flags task pairs with negative transfer

Step 10: src/evaluation/error_analysis.py

- categorize_errors(predictions, labels, task_config) — assigns each error to one of 6 categories

- Categories: abbreviation, negation_scope, discontiguous, rare_entity, temporal_ambiguity, cross_sentence

After you're done, tell me which evaluation functions need actual task data vs. which can be tested with synthetic data.

PHASE 3 PROMPT — Use After Phase 2 Is Complete

Core implementation is complete. Now create the experiment scripts and configs.

Step 1: Hydra Configs

Create all YAML configs from configs/CLAUDE.md:

- 6 model configs

- 5 task configs

- 6 strategy configs (S1, S2, S3a, S3b, S4, S5)

- Architecture ablation config (A1–A4)

- Token-controlled baseline config

- HP search space config

Step 2: Entry Scripts

- scripts/run_experiment.py — main entry: python run_experiment.py +experiment=s3b_llama8b

- scripts/run_contamination_check.py — Phase 0 contamination audit

- scripts/run_baseline.py — BERT/BioBERT baselines

- scripts/run_gpt4_baseline.py — GPT-4o-mini API evaluation

- scripts/run_inference_bench.py — latency/throughput/VRAM profiling

- scripts/run_probing.py — adapter probing after training

- scripts/generate_paper_tables.py — auto-generates LaTeX tables from results JSON

Step 3: Notebook Templates

Create skeleton notebooks (markdown cells + import blocks, no execution):

- 01_data_exploration.ipynb

- 02_contamination_report.ipynb

- 03_transfer_heatmap.ipynb

- 04_pareto_frontier.ipynb

- 05_probing_results.ipynb

- 06_calibration_plots.ipynb

- 07_error_analysis.ipynb

- 08_token_controlled_analysis.ipynb

After you're done, give me the exact command to run the first experiment (BERT baseline on semeval2017t3, the easiest public task) as a smoke test of the full pipeline.